## Sheet1
Task Name | Start (Date) | End (Date) | Duration (Days)
T1 - Outlining Traviz Idea | 2021-09-20 | 2021-09-22 | 2
T2 - Drafting Proposal | 2021-09-22 | 2021-09-28 | 6
T3 - Create Github For Project | 2021-09-20 | 2021-09-22 | 2
T4 - Gather Requirements | 2021-09-28 | 2021-10-04 | 12
T5 - Create SRS | 2021-10-10 | 2021-10-23 | 12
T6 - Discuss Project Plan | 2021-10-23 | 2021-10-25 | 2
T7 - Produce Use Case Diagram and Use Case Scenarios | 2021-10-25 | 2021-10-27 | 2
T8 - Produce Activity Diagram | 2021-10-27 | 2021-10-29 | 2
T9 - Produce Class Diagram | 2021-10-27 | 2021-10-30 | 3
T10 - Produce Sequence Diagram | 2021-10-30 | 2021-11-02 | 2
T11 - Review and Finalize Modeling Plan | 2021-11-02 | 2021-11-05 | 3
T12 - Create wireframe for website | 2021-11-05 | 2021-11-07 | 2
T13 - Search for location databases | 2021-11-05 | 2021-11-09 | 4
T14 - Code the interface | 2021-11-07 | 2021-11-09 | 2
T15 - Coding each Use case | 2021-11-05 | 2021-11-20 | 15
T16 - Test run of each use case | 2021-11-20 | 2021-11-22 | 2
T17 - Integrate code | 2021-11-22 | 2021-11-25 | 3
T18 - Debugging | 2021-11-25 | 2021-11-30 | 5
T19 - Complete User Acceptance Testing | 2021-11-30 | 2021-12-02 | 3
T20 - Complete Regression Testing | 2021-12-02 | 2021-12-05 | 3
T21- Create and update Documentation | 2021-12-01 | 2021-12-05 | 5
T22 - Project Presentation | 2021-12-01 | 2021-12-07 | 7
Note : Go to Timesheet sheet to see the final project plan with milestones labelled!

## Timesheet
Task# | Task Name | Duration (Days) | Dependencies | Week | Start (Date) | End (Date)
T1 | Outlining Traviz Idea LKWNJFLKWNF | 2 |  | 1 | 2021-09-20 | 2021-09-22
T2 | Drafting Proposal | 6 |  | 2 | 2021-09-20 | 2021-09-26
T3 | Create Github For Project | 2 |  | 3 | 2021-09-20 | 2021-09-22
T4 | Gather Requirements | 10 | T2(M1) | 4 | 2021-10-10 | 2021-10-20
T5 | Create SRS | 3 | T4(M2) | 5 | 2021-10-20 | 2021-10-23
T6 | Discuss Project Plan | 2 | T5(M3) | 6 | 2021-10-23 | 2021-10-25
T7 | Produce Use Case Diagram and Use Case Scenarios | 2 | T1,T6(M2) | 7 | 2021-10-25 | 2021-10-27
T8 | Produce Activity Diagram | 2 | T7(M3) | 8 | 2021-10-27 | 2021-10-29
T9 | Produce Class Diagram | 3 | T7(M5) | 9 | 2021-10-27 | 2021-10-30
T10 | Produce Sequence Diagram | 2 | T9(M4) | 10 | 2021-10-30 | 2021-11-02
T11 | Review and Finalize Modeling Plan | 3 | T8,T9,T10 (M3) | 11 | 2021-11-02 | 2021-11-05
T12 | Create wireframe for website | 2 |  | 12 | 2021-11-05 | 2021-11-07
T13 | Search for location databases | 4 |  | 13 | 2021-11-05 | 2021-11-09
T14 | Code the interface | 2 | T12(M4) | 14 | 2021-11-07 | 2021-11-09
T15 | Set Up Testing Environment | 1 |  | 14 | 2021-11-07 | 2021-11-07
T15 | Coding each Use case | 15 | T11(M5) | 15 | 2021-11-05 | 2021-11-20
T16 | Test run of each use case | 2 |  | 16 | 2021-11-20 | 2021-11-22
T17 | Integrate code | 3 | T16(M7) | 17 | 2021-11-22 | 2021-11-25
T18 | Debugging | 5 |  | 18 | 2021-11-25 | 2021-11-30
T19 | Create and update Documentation | 5 |  | 19 | 2021-12-01 | 2021-12-05
T20 | Project Presentation | 7 | T19(M9) | 20 | 2021-12-01 | 2021-12-07